Global Adventures Trip Review and Approval Process

Step 1:  Preliminary Proposal and Risk Assessment

Leader provides the Global Adventures (GA) chair(s) with a high-level summary of the planned trip itinerary, including all significant activity-specific, international and country specific and combined hazards and risk factors, first as a half page or less written summary, and your risk assessment table using the Global Adventures Master Risk Matrix (template here) including your risk rating, an explanation of the risk rating, and risk mitigation/management steps.

Once the GA Committee approves this preliminary trip proposal, the leader can go on to develop the detailed proposal (incorporating any modifications that the committee requests).  If the GA Committee determines that the risk remains unacceptably high even with the proposed measures, they may reject the proposal (with detailed explanation) and the leader may modify and re-submit a modified version.  The leader always retains the right to appeal a rejected proposal.

For low risk trips this review step may take a month to complete, because the committee needs to receive proposals the first week of the month for the monthly meeting coming up on the third Monday of the month to allow the committee to complete their reviews.  This could potentially take even longer if multiple proposals are under consideration at the same time.  High risk trips could take longer depending on the complexity of the trip, the experience of the leader with preparing proposals, and the number of details that the committee deems need revision.

Templates, a proposal checklist, and examples for the Preliminary Proposal and Risk Assessment can be found here.

A) Enhanced Review for Higher Risk Trips

For trips that have high risk elements, the GA Committee may request independent review (by an expert and/or by the leadership of the relevant activity committee) of the itinerary and risk assessment to further assess the adequacy of the risk mitigation measures before completion of step 1.  These reviews, if called for, will be carried out by two Mountaineers outside of the Global Adventures committee who have a high level of experience and expertise with the activity in an international context.  The input of the reviewers will be incorporated into the Preliminary Proposal, Risk assessment and mitigation measures and the preliminary proposal will be submitted to the GA Committee.  If judged necessary by the GA Committee, the Mountaineers VP of Operations and/or Risk Management Committee may also be asked to weigh in on the decision whether to approve the trip to go forward to the detailed proposal stage.    Trips that are judged to carry excessive risk even after the leader’s best risk mitigation measures may be denied.  A leader whose proposal has been denied may appeal the decision for further discussion.

Step 2: Detailed Proposal and Budget

Upon Step 1 approval, the trip leader develops and submits the following documents to the GA chair(s)1:

- Detailed itinerary and trip description

- Trip budget with Proposed Trip Price

- Summary of the leader’s experience relative to the proposed trip.

- Application and Trip Agreement forms (on the templates using the requested markup instructions)

GA Committee does a detailed review of these documents.  While all committee members are expected to perform the review and provide comments, one or two individuals with particular expertise in the activity and destination may be assigned primary responsibility for the review, and one may be outside of the Committee, depending on the expertise required.   A checklist has been developed to document the completion of the review steps.

This step could take 2 weeks to a month depending on the complexity of the proposal and questions raised.

Templates, a proposal checklist, and examples for the Detailed Proposal can be found here.

Step 3.  GA Committee Approval or Denial.

The Committee will iterate back and forth with the leader until all Committee and independent reviewer questions and concerns have been addressed.  The GA Committee Chair(s) will be the final arbiter of any differences of opinion, with the top priorities always being safety, management of risk exposure of the participants, leader and Mountaineers, and value delivered to participants.  The final decision and rationale will be documented and communicated to the prospective trip leader and all proposal docs archived in Global Adventures Proposals on the Mountaineers website (viewable only by GA committee members and approved leaders).

Step 4: Final reviews and approvals

Low/Moderate Risk Proposals:  The Global Adventures Committee has final approval authority for proposals with low to moderate risk elements, based on thorough completion of the process steps described above.

High Risk Proposals:  Any proposal with high risk elements will first be vetted through the Global Adventures committee through Step 3, and may be sent to the Mountaineers Risk Management Committee or COO including a link to the appropriate proposal documents on the GA committee page of the Mountaineers website.  Upon review of the risk assessment and other trip details, the RMC or COO may decide to consult with or other parties at their discretion, before making a final decision to approve or to push the proposal back to GAC for specific amendments.   Their suggested changes will be evaluated by GAC and the trip leader for potential revision of the trip, and assuming GAC approval of the modified proposal, final trip proposal documents will be archived on the GA committee page of the Mountaineers website.

Who then circulates to the GA committee

Historically these have been trips that spend an extended time at altitudes over 15,000 feet, but high risk could be associated with other hazards – see the Global Adventures Master Risk Matrix for definitions.