## Sheet1
Story ID | Story Name and Description | Points | Tags | System | Priority | Status | Comments
253 | Improve Events/Calendar Functionality for Program Centers: Allow volunteers to request rooms at the Seattle and Tacoma Program Center directly online (no email, no separate form to submit… super easy). In addition to all of the info needed for the room reservation, the room rental will include a rich text field to describe the event. Also improve the calendar and individual event view. | 8 | Events | Plone Salesforce | High | Expected completion end of Jun 2014
145 | Install EventBrite Salesforce App: We have decided to use EventBrite for online event ticket sales and may also use it for lodge reservations. We need to integrate it into Salesforce and create a web design for our EventBrite account. We will use links to EventBrite in Plone events and blog posts. | 2 | Events | Salesforce | High | Expected completion end of Jun 2014
288 | Develop Process to Clone Production and Copy to Staging/Testing: Needed for projects that require a good working copy of our website data for thorough development and testing. | ? | Infrastructure | Plone | High | To be done with first project that requires it.
163 | Import Trip Activity History: Import trip activities from iMIS that happened before Jan 1, 2014 or are closed in iMIS into Plone and Salesforce. | ? | Activities Data Migration | Plone Salesforce | High
165 | Import Trip Activity Roster History: Import rosters for activities from iMIS that happened before Jan 1, 2014 or are closed in iMIS into Plone and Salesforce. | ? | Activities Data Migration | Plone Salesforce | High
168 | Import Course History: Import courses not already import into Plone. | ? | Courses Data Migration | Plone Salesforce | High
170 | Import Course Roster History: Import course rosters for courses that have not yet been imported into Plone. There are only graduates and students whose status is expired. | ? | Courses Data Migration | Plone Salesforce | High
176 | Import Course Activity History: Import course activities (lectures, field trips and seminars) from iMIS that happened before Jan 1, 2014 or are closed in iMIS into Plone and Salesforce. | ? | Activities Courses Data Migration | Plone Salesforce | High
177 | Import Course Activity Roster History: Import rosters for course activities (lectures, field trips and seminars) from iMIS that happened before Jan 1, 2014 or are closed in iMIS into Plone and Salesforce. | ? | Activities Data Migration | Plone Salesforce | High
181 | Import Donation Transaction History: Import transactions from IMIS into Salesforce for donations made in the last 36 months. | ? | Accounting Donation | Salesforce | High
131 | Automate Account Code Assignment for Accounting Reconciliation: Have Salesforce provide account and sub-account numbers in reports for accounting reconciliation. For most items (membership, courses, purchases) account numbers are looked up automatically. For donations, this may be overridden by the user specifying an account to which the gift is restricted. Do this in a way that our chart of accounts may be edited (some added and some retired). | 8 | Accounting | Salesforce | High
266 | Prevent Back-dated Salesforce Transactions: Accounting systems are generally set up so that you cannot change transaction dates. Salesforce, not being an accounting-based system, allows this. TBD how to handle - prevent or notify. | ? | Accounting | Salesforce | High
198 | Automate Refunds: When a payment is refunded in Stripe, SF is updated automatically. | ? | Accounting | Salesforce Stripe | High
289 | Create a UI for Staff to Process Refunds in Plone: Create an interface where staff can process a refund for memberships, activities, courses, and purchases in Plone. | ? | Infrastructure | Plone Salesforce Stripe | High
290 | Create a Calculation for UTC Date in Salesforce: This calculation would convert the Created Date to the UTC date. This allows us to filter accounting reports using normal Salesforce conventions (e.g. Today, Yesterday, Last Week, etc.). Needed for reconciliation with Stripe (payment processor) reports. | ? | Accounting | Salesforce | High
n/a | Complete Email Confirmation and Notification Setup: We completed roughly half of the email confirmations required for launch. We've got another dozen or so to complete. | 5 | Activities Courses Donations Membership | Staff Only | High |  | Staff only, no developer help needed unless we have problems or questions.
134 | Automatically Assign Leader Badges: Automatically assign/remove badges to leaders based on them being a leader for a committee. Need to add a "Leader Badge Assigned" field to the Committee content type. | ? | Badges Committees | Plone Salesforce | High
147 | Course Roster and Course Template Roster Graduate Functions: Course leaders will be able to see a Master Course Roster that "lives" with the Course Template. This roster is composed of all of the individual Course Rosters including the course roster(s) that will imported. When changes are made to an individual Course Roster, changes are pushed to the Master Course Roster. When changes are made to the Master Course Roster, changes are pushed to the appropriate individual Course Roster. We need this roster to: - Graduate students individually or in a batch. - Extend student status individually or in a batch. - Convert graduate back to students status individually or in a batch. | 8 | Courses | Plone Salesforce | High |  | Biggest part if bulk graduate.
267 | Improve Instructor Registration: We need some improvements to Instructor registration, canceling, and viewing: - Add "Instructor Prerequisite Badges" to Course Templates - Add "Instructor Prerequisite Badges" to Course - Show the Instructor registration option in the registration portlet on the Course View for those qualified - Add "My Course Instruction" and "My Course Instruction History" sections to My Profile. | ? | Courses | Plone Salesforce | High
276 | Add Fields to Course Template and Course: To aid with course faceted searches, add these field to the Course Template and Course content types: - Change "Course Subtype" to "Climbing Course Subtype" - Add "Paddling Course Subtype" - Add "Skiing/Snowboarding Course Subtype" | ? | Courses | Plone Salesforce | High
296 | Add Checkbox for "Single Activity" Courses: Add a "This is a single activity course" checkbox to the Course Template (enter/edit) and Course (inherited and editable) content types of courses where there is ever only one activity/session. If this box is checked, display the message, "This course has only one activity, see the course description for more details." in the "Course Requirements" tab. | ? | Courses | Plone | High
120 | Merge Duplicate Member Records in Plone and Salesforce: Create a process that allows staff to merge two records that are for the same member or guest so that both the Plone and Salesforce records are updated/in sync. | ? | Infrastructure | Plone Salesforce | High
291 | Add Staff UI to Connect Existing Members in a Family: Add an 'Add existing contact' button on the membership page which is visible to staff only. It should bring up a dialog with a form to select a contact and set its head family member. This form should show an error if the selected user already has a current membership. | 2 | Infrastructure | Plone Salesforce Stripe | High
ticket | Default to Logged In User When Scheduling an Activity: When scheduling an activity, default to the logged in user if they are on the sponsoring committee as a leader. | ? | Activities | Plone | High |  | Ticket #683. The first implementation of this had a bad side effect, so we are working on an alternative that will work properly.
ticket | Move the Edit or Cancel Link Column on Rosters: Move the column of Review/Edit/Cancel links from being at the far right of the roster view to the to be the second column, just after the person's name. This will make roster management much easier. | 0.5 | Activities Badges Committees Courses | Plone | High |  | Ticket #720.
ticket | Remove Age Column from Roster Downloads: We have notice if the person is "Under 18" so we really so need the age column and it is relatively sensitive information. | 0.5 | Activities Badges Committees Courses | Plone | High |  | Ticket #721.
ticket | Fix "Open for registration?" Radio Buttons: Fix the these radios buttons so that when a user chooses the "Only activities open for registration" radio button, it shows selected and the "All activities" shows unselected. | ? | Activities | Plone | High |  | Ticket #679. Note that choosing the radio buttons for this functionality works, even though it is not reflected in the radio buttons themselves.
279 | Properly Handle Re-tries on Failed Commits in Plone-Salesforce Sync: Determine the best scheme for handling failed Plone-to-Salesforce sync (e.g. try again after a delay, put it in a sync queue backlog which can be manually launched). We have quite a robust sync system, but this is one loophole that we haven't closed - leaving items un-synced isn't desirable. | ? | Infrastructure | Plone Salesforce | High
103 | Log Contact Changes Synced from Salesforce to Plone: Provide a logs of changes during the nightly Salesforce-to-Plone sync. This will provide an indication if something unexpected gets changed, it will help verify that the sync is working, and it will also provide troubleshooting info in case something goes wrong. | ? | Infrastructure | Plone Salesforce | High
273 | Show Registration Opening and Closing Dates and Times: For activities and courses, add the registration opening and closing dates and times to the registration portlet and search results: - If registration not yet open, show "Registration Opens {Reg_Open_Date_Time} - If registration is open, show "Registration Closes {Reg_Close_Date_Time} - If registration is closed, show "Registration Closed {Reg_Close_Date_Time} | ? | Activities Courses | Plone | High |  | If it's not too difficult, we may want to "move" the publish open and expiration dates to the Course "Details" tab and call them Registration Opens and Registration Closes.
270 | Group Course Rosters and Show Waitlist Position: If the person is on the waitlist, show their position on the waitlist (e.g. "Waitlist (2)" to indicate that person is second on the waitlist). Group the course roster by Registration Status in this order: (1) Registered, (2) Waitlisted, and (3) Canceled. Disable sorting by the Registration Status, but allow sorting within the groups by the other columns. | 2 | Courses | Plone | High
61 | Import Book and Merchandise Content from Acumen: Import book and merchandise information from Acumen, our mountaineersbooks.org catalog and inventory system, to the Plone Book and Merchandise content types. Staff will run the Acumen-Plone export-import process as needed to update products, inventory, etc. Some research is probably needed here. | 8 | Books Ecommerce Merchandise | Plone Salesforce Acumen | High | Expected completion end of Jun 2014
121 | Fulfillment of Merchandise and Book Sales: When a site visitor purchases merchandise, it will be shipped to them. Requires that we send an email to the right account for fulfilling merchandise and book orders. Books and merchandise will both be fulfilled through our publishing warehouse. | 3 | Books Ecommerce Merchandise | Plone Salesforce Acumen | High | Expected completion end of Sep 2014
123 | E-commerce Shipping and Tax: We need a method to give shipping options, calculate shipping and calculate tax for an order that contains books and/or merchandise. | 20 | Books Ecommerce Merchandise | Plone Salesforce Acumen | High | Expected completion end of Sep 2014
138 | Book View: When viewing a Book, site visitors will see a view that looks like the wireframe and graphic to be provided. | 2 | Books Ecommerce | Plone | High | Expected completion end of Sep 2014
139 | Merchandise View: When viewing a Merchandise item, site visitors will see a view that looks like the wireframe and graphic design to be provided. | 2 | Ecommerce Merchandise | Plone | High | Expected completion end of Sep 2014
141 | Notify Acumen of Orders: When a site visitor purchases a book or merchandise from the site, Acumen, our mountaineersbooks.org catalog and inventory system, will receive notification of the order. | 8 | Books Ecommerce Merchandise | Plone Salesforce Acumen | High | Expected completion end of Sep 2014
284 | Shop Faceted Search: Create a faceted search for book and merchandise content. We won't have a lot of merchandise, so it maybe sufficient to do this only for books (~500 titles in print), and use a collection for merchandise. | ? | Books Ecommerce Merchandise | Plone | High | Expected completion end of Sep 2014
285 | Book Content Type: Update book content type ass needed to support book types/categories. Allow for multiple authors to be chosen from our contacts (members or guests) so we can have a profile and bio for each of them. Note book author on their profile that is linked to a collection of their books. Create group of authors to give permissions for blogs, etc. | ? | Books Ecommerce | Plone Salesforce Acumen | High | Expected completion end of Sep 2014
110 | Member Profile - My Purchases: Members will be able to view the following on their member profile: - Membership fees they have paid and printable receipt for tax purposes - Donations they have made and printable receipt for tax purposes - Course fees they have paid - Activity fees they have paid - Books and merchandise they have purchased | ? | Activities Books Courses Ecommerce Membership Merchandise | Plone | High | Expected completion end of Sep 2014 | We should probably implement for book and merchandise purchases at a minimum.
286 | Member Profile - My eBooks: Add a My eBooks section to profile and necessary functionality so that members and guests may download and manages as necessary the eBooks they purchase from us. Need discovery from Doug Canfield. | ? | Books E-commerce Membership | Plone Salesforce Acmen eBook System? | High | Expected completion end of Sep 2014 | Could be future enhancement.
292 | Import Mountaineers Books Customers: Import Mountaineers Books customers from Acumen to Plone and Salesforce. | ? | Books Membership | Plone Salesforce Acumen | High | Expected completion end of Sep 2014
52 | Safety/Incident Report: Leaders will be able to create and edit an incident report for an activity they have led. Incident reports provide confidential information and are only visible to Mountaineers staff. When an incident report is created or changed, it is emailed to everyone on the Safety Committee and anyone with the Chair position on the sponsoring committee. Data will be synced to Salesforce for reporting and historical archives. | 3 | Activities | Plone Salesforce | High |  | Depending on the ultimate need, it may be best to do this with a PFG form. Current implementation is a "mailto" link.
184 | Activity Search with Map View: Site visitors will be able to browse and search Activities using various criteria, and see the results on a map. | 3 | Activities Maps | Plone | High
287 | Routes & Places Search with Map View: Site visitors will be able to browse and search Route & Places using various criteria, and see the results on a map. | 3 | Routes & Places Maps | Plone | High
277 | Create a "Mountaineers Members" Group: Make a group that is comprised of contacts who meet these criteria: - Membership Type is Adult, Family, Student, Senior, Peak Society, Honorary, Life, Staff - Membership Status is Current or Grace Period We'll use this group to allow access to a Member Benefits page, mountaineers.org/membership/benefits, with discount codes and instruction for obtaining members benefits. We may want two Member Benefits pages, one that shows to the "Paying Members" group and one that shows to everyone else. | ? | Membership | Plone | High
31 | Activity Feedback: Members who participate in an activity will have access to a form or survey where they may provide anonymous feedback on the activity and the leader. A link to this form will be emailed to participants after the activity is completed. | ? | Activities | Plone Salesforce | Medium
38 | Course Feedback: Members who participate in a course will have access to a form or survey where they may provide anonymous feedback on the course and the leader. A link to this form will be emailed to participants after the activity is completed. | ? | Courses | Plone Salesforce | Medium
271 | Add Carpooling Opt-in: Add a carpooling opt-in in checkbox on the My Profile Preferences tab with a plain text entry box for "carpool notes." If the member or guest opts in, display a "Subaru Outback" icon along with the person's "carpool notes" on their profile page and popup. | ? | Membership | Plone Salesforce | Medium
127 | Allow Anyone to give a Gift Membership: Allow anyone to give a gift membership to anyone else. Can be for any paying membership. Can be for a new membership or a renewal. | ? | Membership | Plone Salesforce Stripe | Medium |  | High nearer the holidays? Or gift certificates (new story)?
10 | Member Directory: Members will be able to browse and search a directory of all Mountaineers members, most likely a faceted search of the "Mountaineers Members" group. | ? | Membership | Plone | Medium
23 | Member Profile - Bucket List: Each member or guest can create and edit a "bucket list" which is part of their account information. Their list is a list of Activity Templates, Course Templates, Routes & Places, and Badges that exist on the site. Activities and courses affiliated with any of these content types are listed on the "bucket list" page grouped by their content type. An email is sent anytime a new item is added. | ? | Membership | Plone Salesforce | Medium
102 | NPSP Multiple Bucket Model: Tweak the Salesforce NPSP code to allow for multiple bucket accounts to prevent "data skew" issues with the high number of non-affiliated contacts we have. | 5 | Infrastructure | Salesforce | Medium |  | Jeff to ask Matthew, defer to Percolator.
26 | Outdoor Centers: Staff will be able to create and edit properties, which describe Mountaineers lodges and cabins that can be reserved. (Fields for content type to be defined in Google spreadsheet.) | ? | Outdoor Centers | Plone Salesforce | Medium
44 | Outdoor Center Reservations: Site visitors will be able to view the availability of Outdoor Centers and make a reservation. Also need functionality for volunteers to manage group reservations. | ? | Outdoor Centers | Plone Salesforce | Medium
135 | Committee View: When viewing a Committee, site visitors will see a view that looks like the wireframe to be provided. Change the field name on Committee from "Contact" to "Primary Contact." Add a "Show as contact" function to committee rosters (like we did for Courses). Show committee contacts like we do for course and activity view roster tabs. Add rich text description to committee content type for committees to "say who they are and what they do" and advertise volunteer openings and opportunities. Add an image field. | 5 | Committees | Plone | Medium
263 | Committee List View: Create a committee list view for a collection of committees that shows the image, title, summary for each committee, and primary contact name, email and phone. Only show contact info to logged in users. | ? | Committees | Plone | Medium
154 | Develop "Umbrella" Functionality for Activities: Develop functionality much like that for courses for activity programs like Explorers and Venturing Crew, activity outings like Yosemite Climbing and "combo" activities like Hike & Stewardship and Cathedral Rock & Mount Daniel. - An umbrella activity that houses two or more individual activities - The umbrella activity name is chosen by the leader and staff get an email to review - Umbrella activities are found in the Activity Search - The umbrella activity and each individual activity has its own roster with registration like that for courses and course activities - Individual activities and activity rosters are closed per established activity closing procedures - TBD - Umbrella activity closing | ? | Activities Youth | Plone Salesforce | Medium
90 | Install Volunteers for Salesforce: Install the "Volunteer for Salesforce" application. To be done by Mountaineers staff with help from SF developers as needed. Implement the form in the "Volunteer Center" for volunteers to self-report hours that were not from running an activity. This is a minimal implementation whose biggest downside is requiring a user to enter name and email, even if they're logged in, to report their hours. Mountaineers staff can enter volunteer hours in SF for events like Banff. | 2 | Volunteers | Plone Salesforce | Medium |  | We could implement the form in the "Volunteer Center" for volunteers to self-report hours that were not from running an activity. This is a minimal implementation whose biggest downside is requiring a user to enter name and email, even if they're logged in, to report their hours. Mountaineers staff can enter volunteer hours in SF for events like Banff.
187 | Integrate Volunteers for Salesforce with Authentication: Integrate the Volunteers for Salesforce with Plone authentication so that members and guests may report their volunteer hours without having to re-enter their name and email address. | ? | Volunteers | Plone Salesforce | Medium
188 | Integrate Leader Volunteer Hours with Volunteer for Salesforce: Add a rollup to the Salesforce contact profile that integrates our volunteers' hours added via an activity closing with those reported through Volunteers for Salesforce. This will make data reporting easier. | ? | Volunteers | Plone Salesforce | Medium
189 | Member Profile - My Volunteer Hours: Provide a list all volunteer hours reported via the activity closing and self-reported by members and guests. Allow members and guests to self-report and edit their volunteer hours from this page. | ? | Membership Volunteers | Plone Salesforce | Medium |  | To provide more robust reporting, we may want to limit how long an entry may be editable.
283 | Volunteer Preferences: Collect info from members and guests like volunteer skills, interests, shirt/jacket/cap sizes for recognition. This info could be on other pages, maybe the My Volunteer Hours. Page. | ? | Volunteers | Plone Salesforce | Medium |  | Discovery needed, discuss with Chris Williams.
205 | Process Recurring Annual Dues and Monthly Donations by ACH: To process ACH (bank draft, automatic checking/saving account deductions) recurring payments we need to research ACH services for securely collecting and storing bank account information, and to determine how easy it is to setup and use this service like we did for Stripe. | ? | Donation Ecommerce Membership | Plone Salesforce ACH Processor (TBD) | Medium
261 | Add an Awards Badges field to Routes & Places: Add an Awards Badges field to Routes & Places. We'll use this to "link" the awards (aka peak pins) badges to Routes & Places that count towards that award badge. We'll need to use this field to make collections or as a filter in a faceted Activity and Route & Places searches for "Peak Pin" badges. | ? | Badges Routes & Places | Plone Salesforce | Medium
83 | New Member Drip Emails: As a new member, I get a series of welcome emails after joining. Staff can change content of emails. | 2 | Membership | Staff Only Salesforce My Emma | Medium |  | Need to work with My Emma and Salesforce a bit, so we can learn best how to implement this.
n/a | Develop an Activity Dashboard: Create a report or reports in Salesforce that provide the raw data and summary information that is currently provided by our "activity statistics" export for activities (aka trips). | 5 | Activities | Staff Only Salesforce | Medium
n/a | Develop an Course Dashboard: Create a report or reports in Salesforce that provide the raw data and summary information that is currently provided by our "activity statistics" export for courses, clinic and seminars, and their lectures and field trips. | 5 | Courses | Staff Only Salesforce | Medium
n/a | Develop an Events Dashboard: Create a report or reports in Salesforce for events like BeWild, Banff, committee meetings, Meet The Mountaineers, and branch monthly meetings. | 5 | Events | Staff Only Salesforce | Medium
n/a | Develop a Volunteers Dashboard: Create a report or reports in Salesforce that list members and guests volunteers hours that have been reported via the leader activity closing and self-reported. | 5 | Volunteers | Staff Only Salesforce | Medium
n/a | Develop Annual Report Dashboard: Create reports in Salesforce needed to provide statistics for our Annual Report. These may be developed from our "dashboards." | 5 | Activities Committees Courses Events Membership Volunteers | Staff Only Salesforce | Medium
295 | Mobile Optimization: Design the website to be optimized for display and use on mobile devices. This includes graphic and User Experience design needed to implement a responsive theme for various size screen of mobile devices. | ? | Mobile Theme | Plone | Medium |  | Will be a $50k+ project investment. Will ultimately become a set of stories.
77 | Donor Moves Management: Development staff can plan and track major donor cultivation "moves", record donor interests, and analyze major donor efforts. | 5 | Donation | Staff Only Salesforce | Medium |  | What does this mean, what do we need. Mary needs to define.
tbd | Use PloneFormGen for Email: Set up forms using the PloneFormGen for all website emails. This is more friendly to those who use web-based email like gmail. | ? | Infrastructure |  | Medium |  | May be staff only once trained on PloneFormGen. May need some theme for these.
tbd | Allow Files to be Attached to Web-generated Email | ? | Infrastructure | Plone | Low |  | Can upload files and images to website and send links to them. Probably better so info lives on our website, expecailly course materials. Can download roster and use personal email client.
tbd | Add a "Feedback" Button to Every Page: It would be immensely helpful to have a "Feedback" button on every page that lets us quickly notify you about issues when browsing the site, without needing to compose an email (using a web dialog). You can automatically include the current URL, account info, and browser information to help you identify the issues without asking for extra data. | ? | Infrastructre | Plone | Low |  | Can use the share by email (envelop icon) at the top of every page to send the page and suggested edits to info@mountaineers.org.
tbd | Allow Online Photo Submission: Allow logged in users to submit photos online for various uses including Routes & Places and Trip Reports. | ? | Routes & Places Trip Reports | Plone | Low
tbd | Create Slide Show Style Galleries for Routes & Places: Create a slide show style gallery for Routes & Places like the wirefrmae that Darrell Houle designed. | ? | Routes & Places | Plone | Low
tbd | Allow Committee Roster Sharing Within a Branch: For all committees in a branch, allow anyone on any committee roster view and use any other of that barnch's committee rosters whehter the perosn is on the rostr or not. | ? | Committees | Plone | Low
39 | Advanced Course Participant/Student Tracking: Leaders will be able to record attendance, performance, etc. for the participants in their course. Information about each participant is confidential to the leader and the participant. These actions will be done per activity and there is no need for a general course attendance/feedback mechanism, so this is about gathering together the information from all the course activities/participants onto one page. | 5 | Courses | Plone Salesforce | Low |  | Mostly have this with the "review" functionality on the course rosters.
53 | Confidential Notes: Leaders will be able to provide confidential notes on the participants in their activities, visible only to Mountaineers staff and the participant. When a confidential note is created or changed, it is emailed to an editable list of Mountaineers staff. The primary leader of the activity is responsible for giving the feedback. | 3 | Activities Courses | Plone Salesforce | Low |  | The "confidential notes" data field was created as part of Story #85, Closing Activities. This story is about automatically emailing those notes to a pre-determined list of people.
70 | Small Instructional Groups (SIG): Leaders can list activities that are only visible to those course participants in their small instructional group | ? | Courses | Plone Salesforce | Low |  | Can do this a few different ways using course functionality.
92 | Automatic Peak Society Levels: as donors increase their unrestricted giving in a 365-day period, they should automatically be given Peak Society status or bumped up to a higher level as they meet the thresholds. Staff will still be able to bump them up a level (or into Peak Society) manually. (TBD how to handle "downgrades"). | 3 | Donations Membership | Plone Salesforce | Low
97 | Facility Closure Notice: Need a place on the website where we can post an office closure notice for emergencies (e.g. inclement weather). | 3 | Infrastructure | Plone | Low |  | One option is to allow for a pop-up to be displayed when we have a facility notice that needs to be displayed. We did not like the use of a right portlet and putting it in the header might be nice, but hard to program and use. We're putting holiday office closures on the Contact Us page. No need for any special treatment.
109 | Member Profile - Trip Reports: Members will be able to view trip reports and other content they submitted on their profile page. | ? | Membership | Plone | Low
124 | Sync Badge Details for Courses and Activities to Salesforce: Currently we're not syncing badges required or awarded for courses, activities or the corresponding templates. We would want to sync these badge details as part of the course or activity, not as part of the template, so that we have a historical record of the badge details were when the course or activity occurred. Since templates can change, we want to store this info in the course or activity. | ? | Activities Badges Courses | Plone Salesforce | Low
142 | Contributed Photos of Routes & Places: Site visitors will always see an image for a Route/Place. If the Route/Place does include an image, the view will display a fallback image that says something like "Members: help us by contributing a photo of this place!" Regardless of whether the Route/Place includes an image, when viewing the Route/Place the visitor will see a button saying something like "Contribute a photo of this place". This button will take them to a form where they can upload an image, with a title, description, and copyright/credit info. (It needs to be decided whether the button is only be visible to logged in members.) When an image is uploaded in this way, an Image object will be created - perhaps inside the Route/Place in a Private folder where it can be reviewed by staff. [Optional additional phase 2 idea: the image object should be customized to include a GPS location, which would be derived from the photo's EXIF data if available. This would enable the images in the private folder to be shown on a map, which would help staff police the images and cull ones that are not from the right place.] | ? | Routes & Places | Plone | Low
143 | Leaders May Suggest Routes & Places, Course Templates and Course Activity Templates: Leaders will be able to create and edit Routes/Places, Couse Templates and Course/Seminar Activity Templates but not publish them. | 8 | Activities Courses Routes & Places | Plone | Low | Nearly Complete | Course Templates - TBD Activity Templates - DONE Routes & Places - DONE
152 | Activity Waitlists for Activities with a Fee: Implement for activities as we did for courses with a fee | 3 | Activities E-commerce | Plone | Low |  | Most activities are FREE.
278 | Add Cancel Pending status to Activity registration: Add Cancel Pending status to Activity registration and handle cancellation for activities with a fee the same as we did for courses. | ? | Activities | Plone | Low
219 | Hold Activity or Course Roster Space for Specified Time: For activities or courses with a fee, hold a space on a course or activity roster after a person places it in their shopping cart for a time to be specified in site settings. One option is to add a "Processing" Activity/Course Registration Status that is converted to "Cancel" after the specified time. If the person does not pay in this time limit, allow that roster space to be taken by another. If there is a waitlist when the "Processing" status expires, staff is notified that the a person should be added from the waitlist. | 5 | Activities Courses Ecommerce | Plone | Low
293 | Allow Multiple Payments for an Activity: For high-dollar activities like Global Adventures, allow participants to make at least two payment towards the total for the activity. | ? | Accounting Activities E-commerce | Plone Salesforce | Low
155 | Add an Earned Badge to an Activity: Allow a badge to be earned for successfully completing an activity. This is not super important, but could be useful for granting a Stewardship badge and maybe in some other situations. | ? | Activities Badges Courses | Plone Salesforce | Low
156 | Import Waiver History: Import waiver history for members and guests. | ? | Membership Data Migration | Salesforce | Low |  | We only have a set of signed dates and good thru dates in iMIS for each person. We will NOT import to Plone. May import to Salesforce later if needed.
171 | Import Trip Reports: These go with the Route & Places content, but we will only import a subset of our data to Routes & Places. | ? | Activities Data Migration Routes & Places | Plone Salesforce | Low |  | Archive available online in Leader Resources area.
172 | Import Safety/Incident Reports: Import the safety/incident reports that go with activities. | ? | Activities Courses Data Migration | Plone Salesforce | Low |  | Safety committee does not use this data for reporting, they us the emailed information they get from the leaders.
173 | Import Confidential Notes: Import the confidential notes that go with an activity. This is needed only for history and is for Salesforce only. | ? | Activities Courses Data Migration | Salesforce | Low |  | We have this in iMIS and can retrieve as needed.
195 | Import Committee Rosters: History: Import committee rosters for those whose service on a committee has expired. | ? | Committees Data Migration | Salesforce | Low |  | We have this in iMIS and can retrieve as needed.
207 | Consider "Endless Scroll" for Faceted Search Results: This eliminates the need for pagination which would be the fallback if JavaScript on the user's local machine is not enabled. | ? | Activities Courses Membership Routes & Places | Plone | Low
214 | My Profile - Registration Notice: Implement the Registration Notice on the My Profile wireframe. | 5 | Activities Courses Membership Routes & Places | Plone | Low |  | We have really good notice on the top of the profile page, so we probably don't need this in the left nav as it was designed.
220 | Create Salesforce Code to Save Membership Prices to the Membership Object: This is useful for membership renewal notices, but not required, because we have workarounds for now. | ? | Infrastructure Membership | Salesforce | Low |  | We have to enter membership process 2-3places when changes are made, so this would make that easier and errors less likely.
227 | Template Deletions: We need to decide whether an activity or course or its template (including Routes & Places) should be able to be deleted in Plone, and what to sync to Salesforce if it is. Ideally, we should prevent template deletion, but instead have a way to "retire" the template. Similarly we might want to prevent deletion of any activity or course that has people on its roster. Even if any of the above objects are deleted, the corresponding record in Salesforce probably shouldn't be deleted in most cases. So we need to decide what to do with the sync - set a status value to "Deleted in Plone" or the like. | ? | Activities Courses | Plone Salesforce | Low
230 | Member Renewal Notices: Automatically lookup renewal cost from Salesforce Products table for membership renewal reports. We are currently using a workaround of pulling renewal costs from custom setting. | ? | Infrastructure Membership | Salesforce | Low
264 | Remove Password Field from Salesforce Contact: This is no longer needed, because we did not import passwords from iMIS. It is currently hidden, but needs to be fully removed. | 1 | Infrastructure | Salesforce | Low
268 | Show Prices for Activities and Courses in Search Results: Show prices for courses in search results listings (faceted searches, collections, folder listings). If the course is free, show FREE. Do need to show both member and guest price. Show prices for activities in search results listings (faceted searches, collections, folder listings). If the activity is free for members and guests, do not sow any fee info. If one of them has a price, show that price: for members only, Show "Members $1,000"; for members free and guests with fee "Members FREE, Guests $25." | ? | Activities Courses | Plone | Low
269 | Create UI for Staff to Update Home Page Sliders: Currently these are hardcoded and require developers to update them. | 3 | Home Page Theme | Plone | Low
274 | Prevent Plone from Retaining the Last-viewed URL After a User Logs Out: In Plone if you are on a page and you log out, and then log back in, it returns to the page you started on. In this case that happens to be the profile of the first user (if the second user has permission to view it). I don't really consider this a security issue since permissions are respected, but it is mildly confusing and I can see how it might be suboptimal on shared computers if the first user logs out and doesn't close the window before another user tries to log in. We can stop Plone from retaining the old URL after someone logs out, but it'll take a bit of digging. | ? | Infrastructure | Plone | Low
280 | Handle Plone Copied Items in Plone-Salesforce Sync Properly: Disable copy (or change how it works) of syncable items in Plone with child object (e.g. Course Template, Activity Templates, Routes & places, Courses, Activities). | ? | Infrastructure | Plone Salesforce | Low |  | We don't want copies in Plone, but may want to "clone" as a starting point.
282 | Install CongaMerge for Salesforce: CongaMerge is a pay service that intrgrate Salesforce reports with mail merge templates. Has a free trial. Website: http://www.congamerge.com. | ? | Infrastructure | Salesforce CongaMerge | Low |  | Will use Salesforce reports and Word Merge. If this proves too difficult or time-consuming, we'll consider installing CongaMerge.
199 | Import Current Transactions: Need to consider activities (e.g. Global Adventures) and courses with a balance due. This may be only a Mountaineers consideration, so no developer help will be required. But we do need to decide how best to handle these. | ? | Activities Courses Data Migration | Staff Only | Low |  | We can look these up in or report on them from iMIS as needed.
22 | Trip Reports - Advanced: Course participants including leaders can create and edit a trip report for an activity they have taken. Trip reports provide general information and will be visible to anonymous site visitors. This is a much more data rich and feature rich version of trip reports. | ? | Activities Courses Routes & Places Trip Report | Plone Salesforce | Low |  | Can implement if the current implementation is insufficient.
149 | Youth can be Registered for the Venturing program Which Has a Monthly Recurring Cost: The price will be different based on membership type - guests will pay a higher price than members. As long as they maintain their subscription, the youth gets a Venturing badge which allows them to sign up for activities where the Venturing badge is a prerequisite. | ? | Youth | Plone Salesforce | Low |  | Could be done with "umbrella activity" functionality with a monthly activity that has a fee.
150 | Venturing Trips with Activities Managed by Staff and Optional Paid Activities: Venturing trips can be week long trips with multiple activities each day. We're assuming these will be set up as courses containing the daily activities. Some activities have an additional fee associated - can courses contain activities with fees? In addition, other activities will be assigned by the program administrator rather than chosen by the participants -- is it possible to not allow participants to choose activities? | ? | Activities Youth | Plone Salesforce | Low |  | Currently using courses to mane this. Could switch to "umbrella activity" functionality when completed.
211 | Accounting Reconciliation Reports In Terms of Credits & Debits: Currently Salesforce revenue reports just show money received for various categories, but does not put things in terms of credits and debits within each account/sub-account. This is the easiest format for accounting to use. | ? | Accounting | Salesforce | Low
272 | Improve roster downloads: Move the "Download Roster" button to the bottom of the roster next to the "Email" button. Only download records for those whose button is checked. - Committee Rosters - Activity Rosters (note may want to have a "Select/Deselect All" for each group) - Course Rosters (note may want to have a "Select/Deselect All" for each group, see Story #270) - Badge Rosters (may not need, we will probably get badge rosters via SF reports) | ? | Activities Badges Committees Courses | Plone | Low
57 | GPS Location: Staff and leaders will be able to create and edit GPS locations. Information about the GPS location will include: - GPS coordinates (required - can be typed in or selected from a map) - Name (required) - Description (optional) - Image (a photo - optional?) - Rich text, which may contain multiple images, giving a full description of the location (optional) | 2 | Maps | Plone | Low |  | The built in "Location" type may be sufficient for this, although it does not include image or rich text fields. We also mostly just need to integrate a map with other kinds of content like Routes & Places.
65 | Course Search with Map View: Site visitors will be able to browse and search courses using various criteria, and see the results on a map. | ? | Courses Maps | Plone | Low |  | This needs discussion, we have no geolocation data for courses so it is not at all obvious how this would work. The course list view already lets you screen by branch, which has something to do with location.
294 | Create a UI for Staff to Process Checks and Cash in Plone: This is needed to process membership annual dues, activity fees and course fees paid by check or cash, mailed or in person. | ? | Infrastructure | Plone Salesforce | Low
73 | Donor Recognition: Staff can enter a "Preferred Donor Listing" name for donor recognition, and export lists of donors and gifts including this name. | 1 | Donations | Salesforce | Low |  | Donors may enter "Preferred Donor Listing" for each donation. This may be all we need, and this may be done.
93 | Split Matching Gifts: Create functions for staff to enter gifts from employers who match cash giving and/or volunteer hours, specify that a check matches multiple cash/hours gifts from donors, and what portion is for each, without having to split the check into multiple transactions. | 5 | Donation | Salesforce | Low |  | Can do with multiple "opportunities" in Salesforce.
35 | Waive Course Fee: Staff can waive a fee (activity, course, membership) for members who have scholarships, and for other exceptional cases. Provide a special UI for staff to do this other than Roster edit tab. | ? | Courses | Plone | Low |  | Can be done by using "Add person to roster" functionality.
80 | Donor Thank You Letters: Staff can export batches of gifts needing thank you letters, produce and send the letters. We may need to send different letter templates based on campaign, fund, in honor of, etc. | ? | Donations | Salesforce | Low |  | Will use Salesforce reports and Word Merge. If this proves too difficult or time-consuming, we'll consider installing CongaMerge.
Note on C1: Points is the system we use in agile development to determine how much time and effort are needed to complete a story. As a guage, devekoping our new website took us an entire year and 690 story points to develop. That's ~57 points/month which is running developoment at "full throttle." This is a pace we will not maiantain for our future enhancements, because of budget and time constrants.
Note on E1: Plone is an open source CMS (Content Management System) on which our website was developed. Salesforce is pay for service (with deep discounts for nonprofits) CRM (Customer Relationship Management System) that our staff uses for reporting and donor and key partner management. Stripe is our credit card payment processor. Acumen is our books inventory management system.